## Risk Analysis
ID | Risk | Likelihood 1 – Unlikely 4 – Very Likely | Consequence | Impact 1 – Low 4 – High | Risk Factor Likelihood x Impact | Mitigation Strategies
1 | Poor planning | 3 | Project overruns / Fails to meet milestones | 4 | 12 | Use project management software / Follow a planning process
2 | Loss of work | 3 | Work must be repeated | 4 | 12 | Use back-ups / Cloud storage / Version Control
5 | Difficulty intergrating technologies | 4 | Chosen technologies must be reconsidered | 3 | 12 | Create prototypes and integration tests
14 | Persistant programming bugs | 3 | Tasks take longer to complete than planned | 3 | 9 | Provide lenient development time to address bugs
6 | Unclear goals | 2 | Unnecessary work may be completed | 4 | 8 | Clearly define needs and scope of project
7 | Chosen technology is unsufficent | 2 | Chosen technologies must be reconsidered | 3 | 6 | Create prototypes and integration tests
11 | Developed solution is not suited to live environments | 2 | Solution may require rework | 3 | 6 | Ensure requirements are clear
13 | Digital developer environment is not suitable | 2 | Tasks take longer to complete than planned | 3 | 6 | Ensure environment is set-up beforehand and is comfortable
15 | Underestimated difficulty of task | 2 | Tasks take longer to complete than planned | 3 | 6 | Allow time near end of project to catch-up
16 | Solution is cost in-effective | 2 | Solution may require rework | 3 | 6 | Ensure requirements are clear
3 | Loss of back-ups | 1 | Work must be repeated | 4 | 4 | Use multiple back-ups
9 | Users unavailable for testing | 4 | Solution cannot be verified by real users | 1 | 4 | Select evaluation strategy that does not require live users
10 | Requirements are insufficent | 1 | Solution may require rework | 3 | 3 | Ensure requirements are clear
8 | Project requirements change | 1 | Previous plans may become irrelevant | 2 | 2 | Follow an adapatable workflow such as Agile
12 | Prolonged loss of access to online resources | 1 | Supplementary research cannot be completed | 2 | 2 | Complete research sub-stages early
4 | Unclear commit messages | 1 | Reviewing code later may become difficult | 1 | 1 | Follow a standard or convention for commit messages

## Risk Chart
Impact
|  | 1 | 2 | 3 | 4
Likelihood | 1
2
3
4