## Sheet1
|  |  | Plan | Notes
January | 18 | Mon
| 19 | Tue
| 20 | Wed
| 21 | Thu
| 22 | Fri | Paper Gathering
| 23 | Sat
| 24 | Sun
| 25 | Mon | Lit Review
| 26 | Tue
| 27 | Wed
| 28 | Thu
| 29 | Fri
| 30 | Sat
| 31 | Sun
Febuary | 1 | Mon | Lit Review
| 2 | Tue
| 3 | Wed
| 4 | Thu
| 5 | Fri
| 6 | Sat
| 7 | Sun
| 8 | Mon | Requirements/Plan
| 9 | Tue
| 10 | Wed
| 11 | Thu
| 12 | Fri
| 13 | Sat
| 14 | Sun
| 15 | Mon | Prototype
| 16 | Tue
| 17 | Wed
| 18 | Thu
| 19 | Fri
| 20 | Sat
| 21 | Sun
| 22 | Mon
| 23 | Tue | Progress Report
| 24 | Wed
| 25 | Thu
| 26 | Fri
| 27 | Sat
| 28 | Sun
March | 1 | Mon | Sprint 1
| 2 | Tue
| 3 | Wed
| 4 | Thu
| 5 | Fri
| 6 | Sat
| 7 | Sun
| 8 | Mon | Sprint 1
| 9 | Tue
| 10 | Wed
| 11 | Thu
| 12 | Fri
| 13 | Sat
| 14 | Sun
| 15 | Mon | Sprint 2
| 16 | Tue
| 17 | Wed
| 18 | Thu
| 19 | Fri
| 20 | Sat
| 21 | Sun
| 22 | Mon | Sprint 2
| 23 | Tue
| 24 | Wed
| 25 | Thu
| 26 | Fri
| 27 | Sat
| 28 | Sun
| 29 | Mon | Sprint 3
| 30 | Tue
| 31 | Wed
April | 1 | Thu
| 2 | Fri
| 3 | Sat
| 4 | Sun
| 5 | Mon | Sprint 3
| 6 | Tue
| 7 | Wed
| 8 | Thu
| 9 | Fri
| 10 | Sat
| 11 | Sun
| 12 | Mon | Sprint 4
| 13 | Tue
| 14 | Wed
| 15 | Thu
| 16 | Fri
| 17 | Sat
| 18 | Sun
| 19 | Mon | Sprint 4
| 20 | Tue
| 21 | Wed
| 22 | Thu
| 23 | Fri
| 24 | Sat
| 25 | Sun
| 26 | Mon | Catch-up
| 27 | Tue
| 28 | Wed
| 29 | Thu
| 30 | Fri
May | 1 | Sat
| 2 | Sun
| 3 | Mon | Finish Report
| 4 | Tue
| 5 | Wed
| 6 | Thu
| 7 | Fri |  | Hand-in
| 8 | Sat | Presentation
| 9 | Sun
| 10 | Mon | Presentation
| 11 | Tue
| 12 | Wed
| 13 | Thu
| 14 | Fri
| 15 | Sat
| 16 | Sun
| 17 | Mon | Presentation | Presentation Week
| 18 | Tue
| 19 | Wed
| 20 | Thu
| 21 | Fri