## Risk Analysis
ID | Risk | Likelihood 1 – Unlikely 4 – Very Likely | Impact 1 – Low 4 – High | Risk Factor Likelihood x Impact | Mitigation Strategies
1 | Poor management | 4 | 4 | 16
2 | Loss of work | 3 | 4 | 12 | Use back-ups / Cloud storage / GitHub
3 | Loss of back-ups | 1 | 4 | 4
4 | Missed Milestones | 4 | 3 | 12 | Allow time near end of project to catch-up
5 | Unclear commit messages | 2 | 1 | 2
6 | Compications intergrating technologies | 4 | 3 | 12 | Create prototypes and integration tests,
7 | Unclear goals | 2 | 4 | 8 | Clearly define needs and scope of project
8 |  | 1 | 1 | 1
9 |  | 1 | 1 | 1
10 |  | 1 | 1 | 1
11 |  | 1 | 1 | 1
12 |  | 1 | 1 | 1
13 |  | 1 | 1 | 1
14 |  | 1 | 1 | 1
15 |  | 1 | 1 | 1
16 |  | 1 | 1 | 1
17 |  | 1 | 1 | 1
18 |  | 1 | 1 | 1
19 |  | 1 | 1 | 1
20 |  | 1 | 1 | 1